## Burndown Chart
| Estimated | 2017-04-22 | 2017-04-24 | 2017-04-26 | 2017-04-28 | 2017-05-01 | 2017-05-03 | 2017-05-05 | Total hours
Server connection | 8 | [7 empty] | 0
Show trip list when connected | 2 |  |  | 2 |  |  |  |  | 2
Façade design pattern | 5 |  | 5 | [5 empty] | 5
Iterator design pattern | 5 |  |  | 5 |  |  |  |  | 5
Proxy design pattern | 5 |  |  |  | 5 |  |  |  | 5
Observer design pattern | 18 |  |  |  | 18 |  |  |  | 18
MVC design pattern | 9 | [7 empty] | 0
Client GUI | 1 | 1 | [6 empty] | 1
Display triplist in GUI on update | 3 |  |  |  | 3 |  |  |  | 3
Singleton design pattern | 5 |  | 5 | [5 empty] | 5
Display triplist in date interval | 3 |  |  |  |  | 3 |  |  | 3
Junit test for proxy | 4 |  |  |  |  | 4 |  |  | 4
Clean code | 2 | [7 empty] | 0
Actual remaining hours | 70 | 69 | 59 | 52 | 26 | 19 | 19 | 19
Estimated remaining hours | 70 | 60 | 50 | 40 | 30 | 20 | 10 | 0

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 8 | As user I want to connect to server
2 | Critical | 2 | After connecting client to server, current trip list is displayed
3 | Critical | 18 | Customer wants observer design pattern
4 | Critical | 5 | Customer wants proxy design pattern
5 | Critical | 5 | Customer wants iterator design pattern
6 | Critical | 5 | Customer wants façade design pattern
7 | Critical | 5 | Customer wants singleton design pattern
8 | Critical | 4 | Customer require to test proxy
9 | Critical | 9 | Customer wants MVC design pattern
10 | Low | 1 | Different GUI on client computers
11 | Medium | 3 | As client user I want to see a list of tours in a given date interval
12 | Low | 3 | Display triplist in GUI on update
13 | Low | 2 | Customer wants clean code without redundant methods and useless sysouts.

## 22.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Design Client-Server architecture | All | 1 | Done
1 | 1 | Implement server classes | Martin | 2 | Done
1 | 1 | Implement client side | Martin | 2 | In progress
1 | 1 | Test connecting to the server | Marek | 1 | Done
1 | 1 | Document Client-Server architecture | Krzysztof | 2 | In progress
10 | 1 | Create client side GUI | Marek | 1 | Done

## 24.04
PB-ID | ID | Task title | Responsible | Estimated | Status
3 | 1 | Implement Observer design pattern | Marek, Stela | 3 | In progress
3 | 2 | Test Observer design pattern | Marek, Stela | 2 | In progress
6 | 3 | Implement Façade design pattern | Martin | 2 | Done
6 | 4 | Test Façade design pattern | Krzysztof | 1 | Done
6 | 5 | Documennt Façade design pattern | Andreea | 2 | Done
7 | 6 | Implement Singleton design pattern | Andreea | 2 | Done
7 | 7 | Test Singleton design pattern | Andreea | 1 | Done
7 | 8 | Document Singleton design pattern | Andreea | 2 | Done

## 26.04
PB-ID | ID | Task title | Responsible | Estimated | Status
3 | 1 | Implement Observer design pattern | Marek, Stela | 7 | Done
3 | 2 | Test Observer design pattern | Marek, Stela | 3 | Done
3 | 3 | Document Observer design pattern | Stela | 4 | Done
2 | 4 | Send trip list to client when connected | Martin | 2 | Done
12 | 5 | Display updated trip list on client GUI | Marek | 3 | In progress
5 | 6 | Implement Iterator design pattern | Andreea | 2 | Done
5 | 7 | Test Iterator design pattern | Andreea | 1 | Done
5 | 8 | Document Iterator design pattern | Andreea | 2 | Done
9 | 9 | General documenntation of MVC | Krzysztof | 2 | In progress

## 28.04
PB-ID | ID | Task title | Responsible | Estimated | Status
9 | 1 | Create packages for MVC design pattern | Krzysztof | 1 | Done
9 | 2 | Update controller classes to folow MVC | Marek | 4 | Done
9 | 3 | Test MVC design pattern | Stela | 1 | Done
9 | 4 | Document MVC design pattern | Krzysztof | 3 | In progress
4 | 5 | Implement Proxy design pattern | Andreea | 2 | Done
4 | 6 | Test Proxy design pattern | Andreea | 1 | Done
4 | 7 | Document Proxy design pattern | Andreea | 2 | Done
0 | 8 | Update previous documentations to follow MVC | All | 5 | Done
3 | 9 | Fix sending and displaying updated trip list | Martin | 3 | Done

## 01.05
PB-ID | ID | Task title | Responsible | Estimated | Status
11 | 1 | Implement showing trips in given date interval | Marek | 3 | Done
8 | 2 | Junit test for proxy design pattern | Martin | 4 | Done
11 | 3 | Fix displaying trips in date interval in GUI | Martin | 2 | Done
1 | 4 | Finnish Client-Server documentation | Krzysztof | 2 | Not started
9 | 5 | Finnish MVC documentation | Krzysztof | 2 | Not started
13 | 6 | Delete reduntant methods and sysouts, clean code | Andreea | 2 | In progress