## Burndown Chart
| Estimated | 2017-04-20 | 2017-04-22 | 2017-04-24 | 2017-04-26 | 2017-04-28 | 2017-05-01 | 2017-05-03 | 2017-05-05 | Total hours
Server connection | 10 | [8 empty] | 0
Show current trip list | 3 | [8 empty] | 0
Client GUI | 4 | [8 empty] | 0
Façade design pattern | 3 | [8 empty] | 0
Iterator design pattern | 3 | 2017-04-24: 3 | 3
Proxy design pattern | 7 | [8 empty] | 0
Remote observer d.p. | 28 | [8 empty] | 0
MVC design pattern | 3 | [8 empty] | 0
Client GUI | 2 | 2017-04-22: 2 | 2
Actual remaining hours | 63 | 63 | 61 | 58 | 58 | 58 | 58 | 58 | 58
Estimated remaining hours | 63 | 55.125 | 47.25 | 39.375 | 31.5 | 23.625 | 15.75 | 7.875 | 0

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 10 | As user I want to connect to server
2 | Critical | 3 | After connecting client to server, current trip list is displayed
3 | Critical | 4 | As client user I want to see a list of tours in a given date interval
4 | Critical | 28 | Customer wants remote observer design pattern
5 | Critical | 7 | Customer wants proxy design pattern
6 | Critical | 3 | Customer wants iterator design pattern
7 | Critical | 3 | Customer wants façade design pattern
8 | Critical | 7 | Customer require to test remote observer
9 | Critical | 3 | Customer wants MVC design pattern
10 | Medium | 2 | Different GUI on client computers

## 20.04
PB-ID | ID | Task title | Responsible | Estimated | Status

## 22.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Client server class diagram | Martin | 0.5 | Not Started
1 | 2 | Implement server connection using sockets | Martin | 3 | Done
1 | 3 | Test server connection | Martin | 2 | In Progress
10 | 4 | Create client GUI | Martin | 2 | Done

## 24.04
PB-ID | ID | Task title | Responsible | Estimated | Status
7 | 2 | Document façade | Andreea | 1 | In Progress
1 | 3 | Start documentation of Client-Server | Krzysztof | 3 | Done
1 | 4 | Client-Server class diagram | Martin | 0.5 | Done
4 | 5 | Simple implementation of remote observer | Marek, Stela | 12 | Done
6 | 7 | Implement iterator design pattern | Andreea | 2 | Done
6 | 8 | Document iterator | Andreea | 1 | Done

## 26.04
PB-ID | ID | Task title | Responsible | Estimated | Status
2 | 1 | Implement displaying trip list | Marek | 3 | Not started
5 | 2 | Implement proxy design pattern | Andreea | 5 | Not started
5 | 3 | Document proxy | Andreea | 2 | Started