## Burndown Chart
| Estimated | 2017-04-22 | 2017-04-24 | 2017-04-26 | 2017-04-28 | 2017-05-01 | 2017-05-03 | 2017-05-05 | Total hours
Server connection | 8 | [7 empty] | 0
Show trip list when connected | 2 |  |  | 2 |  |  |  |  | 2
Façade design pattern | 5 |  | 5 | [5 empty] | 5
Iterator design pattern | 5 |  |  | 5 |  |  |  |  | 5
Proxy design pattern | 5 |  |  |  | 5 |  |  |  | 5
Remote observer d.p. | 22 |  |  |  | 16.5 |  |  |  | 16.5
MVC design pattern | 9 | [7 empty] | 0
Client GUI | 1 | 1 | [6 empty] | 1
Display triplist in GUI on update | 3 | [7 empty] | 0
Singleton design pattern | 5 |  | 5 | [5 empty] | 5
Actual remaining hours | 65 | 64 | 54 | 47 | 25.5 | 25.5 | 25.5 | 25.5
Estimated remaining hours | 65 | 55.7143 | 46.4286 | 37.1429 | 27.8571 | 18.5714 | 9.2857 | 0

## Project Backloog
ID | Priority | Estimated time | Story
1 | Critical | 8 | As user I want to connect to server
2 | Critical | 2 | After connecting client to server, current trip list is displayed
3 | Critical | 16.5 | Customer wants observer design pattern
4 | Critical | 5 | Customer wants proxy design pattern
5 | Critical | 5 | Customer wants iterator design pattern
6 | Critical | 5 | Customer wants façade design pattern
7 | Critical | 5 | Customer wants singleton design pattern
8 | Critical | 5.5 | Customer require to test observer
9 | Critical | 9 | Customer wants MVC design pattern
10 | Low | 1 | Different GUI on client computers
11 | Medium |  | As client user I want to see a list of tours in a given date interval
12 | Low |  | Display triplist in GUI on update

## 22.04
PB-ID | ID | Task title | Responsible | Estimated | Status
1 | 1 | Design Client-Server architecture | All | 1 | Done
1 | 1 | Implement server classes | Martin | 2 | Done
1 | 1 | Implement client side | Martin | 2 | In progress
1 | 1 | Test connecting to the server | Marek | 1 | Done
1 | 1 | Document Client-Server architecture | Krzysztof | 2 | In progress
10 | 1 | Create client side GUI | Marek | 1 | Done

## 24.04
PB-ID | ID | Task title | Responsible | Estimated | Status
3 | 1 | Implement Observer design pattern | Marek, Stela | 3 | In progress
3 | 2 | Test Observer design pattern | Marek, Stela | 2 | In progress
6 | 3 | Implement Façade design pattern | Martin | 2 | Done
6 | 4 | Test Façade design pattern | Krzysztof | 1 | Done
6 | 5 | Documennt Façade design pattern | Andreea | 2 | Done
7 | 6 | Implement Singleton design pattern | Andreea | 2 | Done
7 | 7 | Test Singleton design pattern | Andreea | 1 | Done
7 | 8 | Document Singleton design pattern | Andreea | 2 | Done

## 26.04
PB-ID | ID | Task title | Responsible | Estimated | Status
3 | 1 | Implement Observer design pattern | Marek, Stela | 7 | Done
3 | 2 | Test Observer design pattern | Marek, Stela | 3 | Done
3 | 3 | Document Observer design pattern | Stela | 4 | Done
2 | 4 | Send trip list to client when connected | Martin | 2 | Done
12 | 5 | Display updated trip list on client GUI | Marek | 3 | In progress
5 | 6 | Implement Iterator design pattern | Andreea | 2 | Done
5 | 7 | Test Iterator design pattern | Andreea | 1 | Done
5 | 8 | Document Iterator design pattern | Andreea | 2 | Done
9 | 9 | General documenntation of MVC | Krzysztof | 2 | In progress

## 28.04
PB-ID | ID | Task title | Responsible | Estimated | Status
9 | 1 | Create packages for MVC design pattern | Krzysztof | 1 | Done
9 | 2 | Update controller classes to folow MVC | Marek | 4 | Done
9 | 3 | Test MVC design pattern | Stela | 1 | Done
9 | 4 | Document MVC design pattern | Krzysztof | 3 | Not done
4 | 5 | Implement Proxy design pattern | Andreea | 2 | Done
4 | 6 | Test Proxy design pattern | Andreea | 1 | Done
4 | 7 | Document Proxy design pattern | Andreea | 2 | Done
0 | 8 | Update previous documentations to follow MVC | All | 5 | Done
3 | 9 | Fix sending and displaying updated trip list | Martin | 3 | Not done

## 01.05
PB-ID | ID | Task title | Responsible | Estimated | Status